## arenafund_issues
id | title | body | labels | milestone
PF-01 | Decide hero and subhead v1 | Primary hero: Hear the buyer before you wire. Secondary: Tiny slate. Heavy conviction. Outcome: approved text and variants in flags. | copy,ops | Preflight
PF-02 | Approve sitemap | Home, For Investors, For Founders, Thesis, Process, Team, Disclosures, Account, Profile, Contact, 404, 500. | ops | Preflight
PF-03 | Confirm staging and prod behind CDN | arenafund-stg and arenafund-prod Cloud Run behind Cloud CDN. Health checks pass. | backend,ops | Preflight
PF-04 | Protect main branch | Require PR review and status checks before merge. | ops | Preflight
PF-05 | Create tracking doc | Living checklist in repo or knowledge tool. Owners and dates assigned. | ops | Preflight
PF-06 | Create GitHub labels | copy, design, frontend, backend, compliance, analytics, content, ops. | ops | Preflight
PF-07 | Create GitHub milestones | Week 1, Week 2, Phase 2, Eng Hardening, Data, Content, Validation, Legal, Launch. | ops | Preflight
W1-D1-01 | Define KPIs v1 | Unique visitors, investor leads, founder applies, profile completions, doc uploads, booked intros. | ops,analytics | Week 1
W1-D1-02 | Lock buyer-validation loop diagram | Signal -> diligence with buyers -> allocation -> post-invest GTM. Export PNG and SVG. | design,copy | Week 1
W1-D1-03 | Finalize sitemap and goals per page | Define primary CTA and success metric per page. | copy,design,ops | Week 1
W1-D1-04 | Define feature flags | hero_variant, deal_room_open, show_buyer_quotes. Store under admin/flags. | backend,frontend | Week 1
W1-D1-05 | Create Firestore admin/flags doc | Seed default values. Add rules to restrict to admins. | backend,data | Week 1
W1-D2-01 | Pick typography pair and loading | Select Google Fonts, add preconnect and font-display swap. | design,frontend | Week 1
W1-D2-02 | Define color tokens | Base, surface, text, accent, states. Document contrast checks. | design,frontend | Week 1
W1-D2-03 | Define spacing, radii, shadows | Tokenize in Tailwind theme. | design,frontend | Week 1
W1-D2-04 | Logo lockups v1 | Horizontal, stacked, mono, favicon. Export SVG and PNG. | design,content | Week 1
W1-D2-05 | OG image template and favicon | Reusable OG template in Figma or code. | design,frontend | Week 1
W1-D3-01 | Voice guide one-pager | Tone, do/don‚Äôt, verbs, examples. | copy,content | Week 1
W1-D3-02 | Home copy v1 | Hero, promise, proof strip, process, CTA. | copy | Week 1
W1-D3-03 | Investors copy v1 | Audience, how it works, allocation policy, FAQs, CTA. | copy | Week 1
W1-D3-04 | Compliance notices callouts | Add 506c and CF disclaimers where needed. | compliance,copy | Week 1
W1-D4-01 | Founders page copy | What we back, what we need, apply explainer. | copy | Week 1
W1-D4-02 | Process page copy | Signal to allocation to post-invest GTM. | copy | Week 1
W1-D4-03 | Team page copy | Mani bio short and long, contact routing. | copy,content | Week 1
W1-D4-04 | Disclosures, privacy, terms draft | Legal pages first draft with counsel placeholders. | compliance,copy | Week 1
W1-D4-05 | Two buyer quotes and two caselets | Draft, anonymize if needed, secure approvals. | content,copy | Week 1
W1-D5-01 | Wireframe core pages | Home, Investors, Founders, Account, Profile mobile-first. | design | Week 1
W1-D5-02 | Wireframe support pages | Contact, 404, 500, Disclosures. | design | Week 1
W1-D5-03 | Component inventory | Button, Input, Select, Card, Badge, Alert, Dialog, Toast, Tabs. | design,frontend | Week 1
W1-D5-04 | Wireframe sign-off | Stakeholder review and approval. | ops | Week 1
W2-D6-01 | High-fi comps for core pages | Home, Investors, Founders in desktop and mobile. | design | Week 2
W2-D6-02 | Redlines and specs | Spacing, type scale, state behaviors. | design | Week 2
W2-D6-03 | Comps approval | Stakeholder sign-off. | ops | Week 2
W2-D7-01 | Tailwind tokens wired | Implement brand tokens in tailwind.config.ts. | frontend | Week 2
W2-D7-02 | Install shadcn/ui and base comps | Generate base components, set theme. | frontend | Week 2
W2-D7-03 | Primitive components | Button, Input, Select, Textarea, Checkbox, Radio. | frontend | Week 2
W2-D7-04 | Compound components | Card, Alert, Dialog, Toast, Tabs, Badge. | frontend | Week 2
W2-D7-05 | Auth utilities | RequireAuth and ProfileCompleteBanner. | frontend | Week 2
W2-D7-06 | Feature flag hook | hero_variant, deal_room_open, show_buyer_quotes. | frontend | Week 2
W2-D8-01 | MDX content pipeline | Set up MDX for static content pages. | frontend | Week 2
W2-D8-02 | Build static pages | Thesis, Process, Team, Disclosures, Contact, 404, 500. | frontend | Week 2
W2-D8-03 | Meta titles and descriptions | Unique SEO metadata per page. | frontend,copy | Week 2
W2-D8-04 | JSON-LD schema | Organization, Website, Person. | frontend | Week 2
W2-D8-05 | sitemap.xml and robots.txt | Automate with Next.js route. | frontend | Week 2
W2-D8-06 | Canonical URLs | Set per page and default. | frontend | Week 2
W2-D9-01 | Investor lead form | Fields, validation, toasts, Firestore write, email alert. | frontend,backend | Week 2
W2-D9-02 | Founder apply form | Fields, validation, toasts, Firestore write, email alert. | frontend,backend | Week 2
W2-D9-03 | Server validation on API routes | Return structured errors. | backend | Week 2
W2-D9-04 | Firestore writes for forms | leads and founderApplications with serverTimestamp. | backend,data | Week 2
W2-D9-05 | Email alert to ops inbox | On submit via Gmail API or SMTP relay. | backend,ops | Week 2
W2-D9-06 | Auth flows verified | RequireAuth gating and redirects. | frontend | Week 2
W2-D9-07 | Profile save merge | Persist name, location, accreditation, docs. | frontend,backend | Week 2
W2-D9-08 | ProfileCompleteBanner logic | Show until name, location, accreditation, and one doc exist. | frontend | Week 2
W2-D9-09 | Upload widget guards | Type and 15 MB size checks, progress, error handling. | frontend | Week 2
W2-D9-10 | GCS signed URL PUT and CORS | End to end upload and persist doc entries. | backend,ops | Week 2
W2-D10-01 | Disclosure banners and footer | Add legal notices and links. | frontend,compliance | Week 2
W2-D10-02 | Cookie consent | Banner behavior and policy link. | frontend,compliance | Week 2
W2-D10-03 | GA4 and GTM wiring | Enable BigQuery export. | analytics,backend | Week 2
W2-D10-04 | Event tracking QA | signup_started, signup_completed, profile_saved, doc_uploaded, investor_lead_submitted, founder_apply_submitted, founder_apply_viewed. | analytics,frontend | Week 2
W2-D10-05 | Playwright smoke tests | Auth, profile save, upload, forms submit. | frontend,backend | Week 2
W2-D10-06 | Lighthouse 95+ targets | Desktop and Mobile for key pages. | frontend | Week 2
W2-D10-07 | A11y pass | Keyboard only and contrast. | frontend | Week 2
W2-D10-08 | No console errors | Zero 4xx on load. Fix any. | frontend | Week 2
W2-D10-09 | Promote staging to prod | Tag release and smoke test. | ops | Week 2
P2-CL-01 | Publish buyer quotes | Two quotes with titles and anonymized org if needed. | content,copy | Phase 2
P2-CL-02 | Publish micro caselets | Two short case studies with outcomes. | content,copy | Phase 2
P2-CL-03 | Buyer Council section | Three logos or anonymized badges. | content,design | Phase 2
P2-CL-04 | Sample deal brief template page | Public example of what investors receive. | content,frontend | Phase 2
P2-IF-01 | Gated request allocation brief | Require Account and basic Profile. | frontend,backend | Phase 2
P2-IF-02 | Investor email sequence | Welcome, process, cohort dates, alerts opt-in. | content,backend | Phase 2
P2-IF-03 | Founder email sequence | Thank you, diligence checklist, brief sample. | content,backend | Phase 2
P2-IF-04 | Intro booking link | 15-min call behind Account. | frontend | Phase 2
P2-CM-01 | Pick accreditation verifier | Select vendor and plan integration. | compliance,ops | Phase 2
P2-CM-02 | Manual attestation fallback | Doc upload flow for accreditation proof. | frontend,compliance | Phase 2
P2-CM-03 | Reg CF partner shortlist and outreach | Issuer checklist and marketing review. | ops,compliance | Phase 2
P2-CM-04 | Update Disclosures | Add accreditation and CF language. | compliance,copy | Phase 2
P2-OP-01 | Admin claim flow | Allow specific emails to be admin. | backend,frontend | Phase 2
P2-OP-02 | Leads table with filters | Internal dashboard with notes. | frontend,backend | Phase 2
P2-OP-03 | Founder applications table | Stages and last touch tracking. | frontend,backend | Phase 2
P2-OP-04 | CSV export | Export leads and applications. | frontend,backend | Phase 2
ENG-AN-01 | GA4 events mapped | Tested in Realtime and BigQuery export works. | analytics,backend | Eng Hardening
ENG-AN-02 | BigQuery export verification | Dataset receiving events. | analytics,backend | Eng Hardening
ENG-AN-03 | Error Reporting alerts | Thresholds and notifications set. | backend,ops | Eng Hardening
ENG-AN-04 | Uptime checks | Staging and prod health checks. | ops | Eng Hardening
ENG-CD-01 | Cloud Build triggers | PR to staging, main to prod. | backend,ops | Eng Hardening
ENG-CD-02 | Deploy previews on PRs | Preview URLs for review. | backend,ops | Eng Hardening
ENG-CD-03 | Lighthouse CI on PRs | Budget thresholds added. | frontend,ops | Eng Hardening
ENG-SC-01 | Secret Manager for keys | Move env secrets and mount at runtime. | backend,ops | Eng Hardening
ENG-SC-02 | Least privilege IAM | Tighten GCS and Firestore roles. | ops,backend | Eng Hardening
ENG-SC-03 | Firestore rules review | Validate shapes and ownership checks. | backend,data | Eng Hardening
ENG-SC-04 | GCS lifecycle for uploads | Delete orphaned uploads after 14 days. | ops,backend | Eng Hardening
ENG-PF-01 | Font loading optimized | Swap and preconnect added. | frontend | Eng Hardening
ENG-PF-02 | Image optimization | next/image sizes and priority set. | frontend | Eng Hardening
ENG-PF-03 | Small client bundles | Route splits and server components. | frontend | Eng Hardening
ENG-PF-04 | A11y checks | Focus states, labels, aria. | frontend | Eng Hardening
ENG-ER-01 | Error boundary | Global error handling page wired. | frontend | Eng Hardening
ENG-ER-02 | 404 and 500 pages styled | Custom pages finalized. | frontend | Eng Hardening
ENG-ER-03 | Structured API errors | Consistent error format. | backend | Eng Hardening
DATA-01 | Collections defined | profiles, leads, founderApplications, buyerCouncil, dealBriefs. | data,backend | Data
DATA-02 | Rules validate shapes | Enforce types and ownership. | data,backend | Data
DATA-03 | Indexes updated | Support queries and dashboards. | data,backend | Data
DATA-04 | Secure admin/flags | Restrict to admins group. | data,backend | Data
CNT-01 | Headshots and banner | Select and optimize assets. | content,design | Content
CNT-02 | Logo exports | Lockups and favicon exported. | content,design | Content
CNT-03 | OG images | Home, Investors, Founders templates. | content,design | Content
CNT-04 | Team bios | Mani short and long bios on page. | content,copy | Content
CNT-05 | Buyer quotes and caselets | Finalize text and approvals. | content,copy | Content
VAL-01 | Feature flag hero variants | A and B variants wired. | frontend,ops | Validation
VAL-02 | Two unlisted staging pages | Collect short investor feedback. | ops | Validation
VAL-03 | Pick winner and freeze | Select hero for launch. | ops | Validation
LEG-01 | Privacy and terms review | Counsel review and edits. | compliance,ops | Legal
LEG-02 | 506c disclosures review | Counsel approval of notices. | compliance,ops | Legal
LEG-03 | Cookie banner behavior doc | Capture interactions and storage. | compliance,ops | Legal
ACC-01 | Lighthouse 95+ key pages | Mobile and Desktop targets met. | frontend,ops | Launch
ACC-02 | A11y keyboard only pass | Manual checks complete. | frontend | Launch
ACC-03 | 301 redirects verified | Old to new paths mapped. | frontend,ops | Launch
ACC-04 | Legal copy approved | Final sign-off recorded. | compliance,ops | Launch
ACC-05 | GA4 Realtime events validated | All key events seen in Realtime. | analytics,frontend | Launch
ACC-06 | Error boundary and 404/500 tested | Force errors and verify UX. | frontend | Launch
ACC-07 | No console errors, no 4xx on load | Clean console and network. | frontend | Launch